|  |  |  |  |
| --- | --- | --- | --- |
|  | ASO AC | RIR Meetings | ICANN Meetings |
| February 2024 | Timeline Review and Approval | APNIC 57 (Bangkok) |  |
| March 2024 | Develop Principals Document  Clarify Process for RIR and ICANN consultations |  | ICANN79  (San Juan) |
| April  2024 | Develop Principals Document  RIR Introduction to Review Timeline as part of ASO AC Updates  Public Page on ASO AC with information including timeline and work documents. | ARIN 53 (Bridgetown) |  |
| May  2024 | Develop Principals Document | LACNIC 41 (Panama City)  RIPE88  (Krakow) |  |
| June  2024 | Draft of Principals document for NRO EC review. |  | ICANN80 (Kigali) |
| July  2024 | Final Principals document for stakeholder Consultation |  |  |
| August 2024 | Multi Stakeholder consultation via ASO AC survey begins |  |  |
| September 2024 | Presents principles document and promotes consultation during RIR meetings | APNIC58 (Da Nang) |  |
| October 2024 | Presents principles document and promotes consultation during RIR meetings.  ASO AC to start collecting definitions for common terms to maintain consistency. | LACNIC42 (TBD)  ARIN 54 (Toronto) |  |
| November 2024 | Presents principles document and promotes consultation during RIR meetings and ICANN81 | RIPE 89 (TBD) | ICANN81 (Istanbul) |
| December 2024 | Rough draft policy |  |  |
| January 2025 | Final Draft available to NRO EC for review.  Confirm 30-day window to APNIC meeting for consultation to begin. |  |  |
| February 2025 | Presents draft policy during RIR meetings | APNIC 59 (TBD) |  |
| March 2025 | Presents draft policy during RIR meetings |  | ICANN82 (Seattle) |
| April  2025 | Presents draft policy during RIR meetings | ARIN 55 (TBD) |  |
| May  2025 | Presents draft policy during RIR meetings | LACNIC43  (TBD)  RIPE 90  (TBD) |  |
| June  2025 | **Develops final policy for NRO EC and ICANN Board consideration** |  | ICANN83  (TBD–Europe) |
| July  2025 |  |  |  |
| August 2025 |  |  |  |
| September 2025 |  | APNIC 60 (TBD) |  |
| October 2025 |  | LACNIC 44  (TBD)  ARIN 56 (TBD) | ICANN84  (TBD–APAC or Middle East) |
| November 2025 |  | RIPE 91 (TBD) |  |
| December 2025 |  |  |  |
|  |  |  |  |